## i want you to turn it into an e
Project Title | English-Khmer Transliteration
Level | Task Name | Description | Status
1 | Project Management
1.1 | Project Planning & Scoping | Initial project definition and outline | Completed
1.2 | Documentation | Creation of project reports and documentation | Completed
2 | Data
2.1 | Romanized–Khmer Text Pairs | Obtaining the 28,576 Romanized–Khmer text pairs from Chrea Chanchhunneng | Completed
2.2 | Khmer Dictionary 44k | Utilizing the Khmer Dictionary 44k from Hugging Face for validation | Completed
2.3 | Data Preprocessing | Cleaning and normalizing the text for model training | Completed
2.3.1 | Romanized Text Cleaning | Removing special characters (e.g., !@#$%) from the Romanized text | Completed
2.3.2 | Khmer Text Normalization | Using the khnormal function from the Khmer Spell package to resolve encoding issues | Completed
2.3.3 | Character-Level Tokenization | Tokenizing both Romanized and Khmer text at the character level using TensorFlow | Completed
3 | Model Development & Training
3.1 | Model Training | Training the deep learning model on the prepared dataset | Completed
3.2 | Model Enhancement | Incorporating additional components like bidirectional layers and an attention mechanism | Completed
3.3 | Evaluation | Measuring the model's performance with specific metrics | Completed
3.3.1 | Evaluation Metrics | Applying Token-Level Accuracy, Character Error Rate (CER), and BLEU | Completed
3.5 | Inference & Refinement | Generating and validating model outputs | Completed
3.5.1 | Beam Search Decoding | Using beam search with a width of five to generate five candidate transliterations | Completed
3.5.2 | Dictionary Alignment | Checking candidates against the Khmer dictionary | Completed
3.5.3 | Levenshtein Distance | Computing the edit distance for non-matching candidates | Completed
4 | System Integration
4.1 | Web Interface Development | Building the user interface with Flask | Completed
4.1.1 | Suggested Transliteration Tab | Creating the main display for the top suggestion | Completed
4.1.2 | User Controls | Implementing keyboard shortcuts for accepting (SPACE) and cycling (TAB) through suggestions | Completed
4.2 | Final System Testing | Verifying all components work together as intended | Completed